Longfin Smelt Synthesis draft timeline (October 2016)

- Summer-Fall 2016: Finalize LFS MAST membership and define scope.

- Winter-Spring 2017: Discuss LFS life history knowledge and conceptual model structures.  Settle on conceptual model structure, develop hypotheses, compile datasets. Assign sections/hypotheses and begin analyses.

- Summer-Fall 2017: Finish analyses. Begin drafting manuscript for management/peer review.

- Winter 2018: Finalize manuscript for peer review, begin IEP review. Create Executive Summary and Managers’ briefing.

- Winter-Spring 2018: Complete IEP review of manuscript, submit for publication.

- Spring 2018: Presentation IEP Annual Workshop